## Sheet1
Stationery Amnesty (SA) Milestones
Action | Notes | Deadline
Take a record of each process step throughout the SA activity. | Record your experience. This is so that other colleagues can repeat this project when you are not here or so that you can carry on with other projects and automise this one.
Discuss with line manager- align to existing strategy | Align the SA with existing policy and strategy. This might be procurement or sustainability objectves. ID SA implementation team for pilot.
Send guidance video to SA implementation team.
Meet with SA implementation team. Develop targets and action plan. Assign roles. | This might include procurement, head of admin, stationery cupboard manager. Roles and issues to consider: Communications. Logistics. Storage. Timeframes. Action plans and records of activities for repeatability. To manage this project you might want to consider using Asana a free project management tool
Storage issues: Start hoarding empty paper boxes and lids! | Event day: For storing surplus stationery when the big day comes. YOU WILL ALSO NEED A POSTAL TROLLEY! This is for surplus binders and lever arch files. Until redistribution the items need to be stored also so think about a room or cupboard.
Download communications materials | From GetWarpIt.com & stationeryamnesty.com
Order posters, wall banners and pull up banners | Use downloadable graphics. Before this investment you might want to carry out the first SA on a shoestring to develop the business case. In the long run banners will be a good investment as they act as stand out and passive communications.
If required get graphic designer to edit | You can add your own logos and remove Warp It logos from the downloadable templates if required. Please note Warp It customers you should insert your unique portal address in the appropriate place.
Create pull up banners to place around building using templates | These are a great investment as you can out them in the foyer of each building when they get the SA
Get together stationery amnesty team | 2nd meeting to discuss progress.
Decide which department will get pilot SA | It is a good idea to choose your own department as you have the strongest network
Add SA email signature to staff emails | Obviously this is a voluntary activity. Try and get senior management to participate!
Send all department email | Template can be downloaded from GetWarpIt.com
Put up posters advertising the activity | Staff get poster fatigue quickly so it is important to remove posters after the event. Or if you have time move their locations in the run up to the event.
Host a coffee morning- invite staff to bring surplus stationery | Have the boxes and post trolley available to collect in the stationery
Take pics and upload to social media | Use #stationeryamnesty hastag for best pics- do a prize
Collect all of the returned stationery into one room. | You will find that lever arch files and binders are the most bulky so make sure you have a postal trolley or two ready to store them. A quick and easy way of finding homes for these items is to put themin the foyer of any building with a note "Free to a good home". This works great on university and college campuses or schools. For your KPI and audit purposes; Make sure you record how many you have beforehand and subtract the remainder to get the correct reuse numbers.
Total up all of the different categories. Add assets to reuse system | See this video for a quick way to do this: https://youtu.be/PYjUFb3it-U. You maybe using Warp It, a message board or a spreadsheet to do this. Warp It is the quickest and easiest for auditing and management.
Tell staff how to claim stationery | Either by visiting the store room or claim off the reuse system.
Review the savings that have been made. | Present the savings to the appropriate committee. Get agreement to do an organistion wide SA incremental rollout
Review the process - integrate the process into organisational procedure. | What worked what didn't
Publicise the SA and how well you did. | Content can be downloaded from Warp It site.
Create waiting list of Departments who want an SA | Remember you are creating a buzz by restricting the roll out to one deprtament at a time
Repeat the mode with additional learnings for each department | Review after each event.
Seek to automise the SA. Can the effort be delegated to representntives form each department? | The original organisers should seek to remove themselves from the process so that the SA can continue without them.
After every department review each SA for improvements
Repeat every 1-3 years.